## ITR Status
站点 | 工序 | ITR编号 | 状态 | 工作类型 | 位置 | 里程
Sharjah | Ballast mat | P2225-PS4-GQC-IR-03507-00 | CODE-2 |  |  | CH 06+444 ~ CH 06+512
Sharjah | Ballast mat | P2225-PS4-GQC-IR-04112-00 | CODE-2 | Ballast mat | Sharjah | CH 12+813 ~ CH 12+867
Sharjah | Bottom ballast | P2225-PS4-GQC-IR-03016-00 | CODE-2 | 3016 |  | CH 00+600 ~ CH 01+786
Sharjah | Bottom ballast | P2225-PS4-GQC-IR-03440-01 | CODE-2 |  |  | CH 01+786 ~ CH 01+825
Sharjah | Bottom ballast | P2225-PS4-GQC-IR-02747-01 | CODE-2 |  |  | CH 01+825 ~ CH 04+500
Sharjah | Bottom ballast | P2225-PS4-GQC-IR-03042-00 | CODE-2 | 3042 |  | CH 04+500 ~ CH 06+000
Sharjah | Bottom ballast | P2225-PS4-GQC-IR-03565-00 | CODE-2 |  |  | CH 06+000 ~ CH 06+750
Sharjah | Bottom ballast | P2225-PS4-GQC-IR-03326-01 | CODE-2 |  |  | CH 06+750 ~ CH 07+725
Sharjah | Bottom ballast | P2225-PS4-GQC-IR-03763-00 | CODE-2 | 3763 |  | CH 07+700 ~ CH 08+680
Sharjah | Bottom ballast | P2225-PS4-GQC-IR-03966-00 | CODE-2 |  |  | CH 10+560 ~ CH 11+380
Sharjah | Bottom ballast | P2225-PS4-GQC-IR-03967-00 | CODE-2 |  |  | CH 11+380 ~ CH 12+350
Sharjah | Bottom ballast | P2225-PS4-GQC-IR-04109-00 | CODE-2 | Bottom ballast | Sharjah | CH 12+350 ~ CH 13+160
Sharjah | Bottom ballast | P2225-PS4-GQC-IR-03968-00 | CODE-2 |  |  | CH 13+160 ~ CH 14+360
Sharjah | Bottom ballast | P2225-PS4-GQC-IR-04165-00 | CODE-2 | Bottom ballast | Sharjah | CH 14+360 ~ CH 14+900
Sharjah | Bottom ballast | P2225-PS4-GQC-IR-03045-00 | CODE-2
Sharjah | Bottom ballast | P2225-PS4-GQC-IR-03851-00 | CODE-2
Sharjah | Bottom ballast | P2225-PS4-GQC-IR-03327-00 | CODE-2
Sharjah | Bottom ballast | P2225-PS4-GQC-IR-03742-00 | CODE-2
Sharjah | Bottom ballast | P2225-PS4-GQC-IR-03970-00 | CODE-2
Sharjah | Bottom ballast | P2225-PS4-GQC-IR-03969-00 | CODE-2
Sharjah | Bottom ballast | P2225-PS4-GQC-IR-04164-00 | CODE-2 | Bottom ballast | Sharjah
Sharjah | Bottom ballast | P2225-PS4-GQC-IR-04166-00 | CODE-2 | Bottom ballast | Sharjah
Sharjah | Track laying | P2225-PS4-GQC-IR-03017-00 | CODE-2 | Track laying |  | CH 00+600 ~ CH 01+786
Sharjah | Track laying | P2225-PS4-GQC-IR-03441-01 | CODE-2 | Track laying |  | CH 01+786 ~ CH 01+825
Sharjah | Track laying | P2225-PS4-GQC-IR-02748-01 | CODE-2 | Track laying |  | CH 01+825 ~ CH 04+500
Sharjah | Track laying | P2225-PS4-GQC-IR-03043-00 | CODE-2 | Track laying |  | CH 04+500 ~ CH 06+000
Sharjah | Track laying | P2225-PS4-GQC-IR-03566-00 | CODE-2 | Track laying |  | CH 06+000 ~ CH 06+750
Sharjah | Track laying | P2225-PS4-GQC-IR-03325-01 | CODE-2 | Track laying |  | CH 06+750 ~ CH 07+725
Sharjah | Track laying | P2225-PS4-GQC-IR-03461-01 | CODE-2 | Track laying |  | CH 07+725 ~ CH 08+690
Sharjah | Track laying | P2225-PS4-GQC-IR-03971-00 | CODE-2 | Track laying |  | CH 11+380 ~ CH 12+500
Sharjah | Track laying | P2225-PS4-GQC-IR-04113-00 | CODE-2 | Track laying | Sharjah | CH 12+500 ~ CH 13+325
Sharjah | Track laying | P2225-PS4-GQC-IR-03046-01 | CODE-2 | Track laying
Sharjah | Track laying | P2225-PS4-GQC-IR-03764-00 | CODE-2 | Track laying
Sharjah | Track laying | P2225-PS4-GQC-IR-03324-01 | CODE-2 | Track laying
Sharjah | Track laying | P2225-PS4-GQC-IR-03463-01 | CODE-2 | Track laying
Sharjah | Track laying | P2225-PS4-GQC-IR-03765-00 | CODE-2 | Track laying
Sharjah | Track laying | P2225-PS4-GQC-IR-03743-00 | CODE-2 | Track laying
Sharjah | Track laying | P2225-PS4-GQC-IR-03848-00 | CODE-2 | Track laying
Sharjah | Track laying | P2225-PS4-GQC-IR-03849-00 | CODE-2 | Track laying
Sharjah | Track laying | P2225-PS4-GQC-IR-03972-00 | CODE-2 | Track laying
Sharjah | Track laying | P2225-PS4-GQC-IR-04114-00 | CODE-2 | Track laying | Sharjah
Sharjah | Track laying | P2225-PS4-GQC-IR-04167-00 | CODE-2 | Track laying | Sharjah
Sharjah | MFBW | P2225-PS4-GQC-IR-03015-01 | CODE-2 | MFBW | Sharjah | CH 00+600 ~ CH 01+763
Sharjah | MFBW | P2225-PS4-GQC-IR-02746-01 | CODE-2 | MFBW | Sharjah | CH 01+825 ~ CH 04+483
Sharjah | MFBW | P2225-PS4-GQC-IR-03041-01 | CODE-2 | MFBW | Sharjah | CH 04+483 ~ CH 05+808
Sharjah | MFBW | P2225-PS4-GQC-IR-03567-00 | CODE-2 | MFBW | Sharjah | CH 05+980 ~ CH 06+685
Sharjah | MFBW | P2225-PS4-GQC-IR-03208-01 | CODE-2 | MFBW | Sharjah | CH 06+700 ~ CH 07+725
Sharjah | MFBW | P2225-PS4-GQC-IR-03321-01 | CODE-2 | MFBW | Sharjah | CH 07+730 ~ CH 08+680
Sharjah | MFBW | P2225-PS4-GQC-IR-03668-00 | CODE-2 | MFBW | Sharjah | CH 10+975 ~ CH 11+500
Sharjah | MFBW | P2225-PS4-GQC-IR-03669-00 | CODE-2 | MFBW | Sharjah | CH 11+525 ~ CH 12+300
Sharjah | MFBW | P2225-PS4-GQC-IR-04110-00 | CODE-2 | MFBW | Sharjah | CH 12+350 ~ CH 13+100
Sharjah | MFBW | P2225-PS4-GQC-IR-03875-00 | CODE-2 | MFBW | Sharjah | CH 13+120 ~ CH 14+900
Sharjah | MFBW | P2225-PS4-GQC-IR-03044-01 | CODE-2 | MFBW | Sharjah
Sharjah | MFBW | P2225-PS4-GQC-IR-03787-00 | CODE-2 | MFBW | Sharjah
Sharjah | MFBW | P2225-PS4-GQC-IR-03322-01 | CODE-2 | MFBW | Sharjah
Sharjah | MFBW | P2225-PS4-GQC-IR-03323-01 | CODE-2 | MFBW | Sharjah
Sharjah | MFBW | P2225-PS4-GQC-IR-03568-00 | CODE-2 | MFBW | Sharjah
Sharjah | MFBW | P2225-PS4-GQC-IR-03670-00 | CODE-2 | MFBW | Sharjah
Sharjah | MFBW | P2225-PS4-GQC-IR-03850-00 | CODE-2 | MFBW | Sharjah
Sharjah | MFBW | P2225-PS4-GQC-IR-03878-00 | CODE-2 | MFBW | Sharjah
Sharjah | MFBW | P2225-PS4-GQC-IR-04111-00 | CODE-2 | MFBW | Sharjah
MBZ | Ballast mats | P2216-PMB-GQC-IR-05252-00 | CODE-1 | Ballast Mat | Zone-4 | CH 01+660 ~ CH 01+957
MBZ | Ballast mats | P2216-PMB-GQC-IR-06213-01 | CODE-5 | Ballast Mat | Zone-6
MBZ | Ballast mats | P2216-PMB-GQC-IR-06641-00 | CODE-5 | Ballast Mat | Zone-3 | CH 02+597 ~ CH 03+020
MBZ | Ballast mats | P2216-PMB-GQC-IR-06642-01 | CODE-1 | Ballast Mat | Zone-8
MBZ | Ballast mats | P2216-PMB-GQC-IR-06687-00 | CODE-5 | Ballast Mat | Zone-8 | CH 07+517 ~ CH 07+684
MBZ | Ballast mats | P2216-PMB-GQC-IR-06688-00 | CODE-1 | Ballast Mat | Zone-6 | CH 05+362 ~ CH 06+103
MBZ | Ballast mats | P2216-PMB-GQC-IR-06706-00 | CODE-1 | Ballast Mat
MBZ | Bottom ballast | P2216-PMB-GQC-IR-03876-01 | CODE-1 | BOTTOM BALLAST | WESTERN CHORD | CH 00+424 ~ CH 01+400
MBZ | Bottom ballast | P2216-PMB-GQC-IR-05774-00 | CODE-1 | BOTTOM BALLAST | WESTERN CHORD | CH 01+400 ~ CH 02+468
MBZ | Bottom ballast | P2216-PMB-GQC-IR-04446-00 | CODE-1 | BOTTOM BALLAST | MBZ ZONE 5 | CH 03+500 ~ CH 05+150
MBZ | Bottom ballast | P2216-PMB-GQC-IR-04732-00 | CODE-5 | BOTTOM BALLAST | MBZ ZONE 5
MBZ | Bottom ballast | P2216-PMB-GQC-IR-05769-00 | CODE-5 | BOTTOM BALLAST | Zone-1, MBZ | CH 00+500 ~ CH 01+600
MBZ | Bottom ballast | P2216-PMB-GQC-IR-06228-00 | CODE-5 | BOTTOM BALLAST | MBZ ZONE 5
MBZ | Bottom ballast | P2216-PMB-GQC-IR-06388-00 | CODE-5 | BOTTOM BALLAST | ZONE-06
MBZ | Bottom ballast | P2216-PMB-GQC-IR-06650-00 | CODE-5 | BOTTOM BALLAST | ZONE 1 | CH 01+600 ~ CH 02+450
MBZ | Bottom ballast | P2216-PMB-GQC-IR-06651-00 | CODE-5 | BOTTOM BALLAST | ZONE 3 | CH 02+450 ~ CH 03+500
MBZ | Bottom ballast | P2216-PMB-GQC-IR-06649-00 | CODE-1 | BOTTOM BALLAST | ZONE 1
MBZ | Bottom ballast | P2216-PMB-GQC-IR-06709-00 | CODE-1 | BOTTOM BALLAST | ZONE 1
MBZ | Bottom ballast | P2216-PMB-GQC-IR-06708-00 | CODE-1 | BOTTOM BALLAST | ZONE 1 | CH 00+386 ~ CH 00+500
MBZ | Bottom ballast | P2216-PMB-GQC-IR-06690-00 | CODE-1 | BOTTOM BALLAST | MBZ ZONE 5
MBZ | Bottom ballast | P2216-PMB-GQC-IR-06691-00 | CODE-5 | BOTTOM BALLAST | ZONE- 6,7, 8, 9
MBZ | Bottom ballast | P2216-PMB-GQC-IR-06818-00 | CODE-1 | BOTTOM BALLAST | ZONE-01
MBZ | Bottom ballast | P2216-PMB-GQC-IR-06787-00 | CODE-1 | BOTTOM BALLAST | ZONE- 6,7, 8, 9 | CH 05+150 ~ CH 08+875
MBZ | Bottom ballast | P2216-PMB-GQC-IR-06883-00 | CODE-1 | BOTTOM BALLAST
MBZ | Bottom ballast | P2216-PMB-GQC-IR-06884-00 | CODE-1 | BOTTOM BALLAST |  | CH 08+875 ~ CH 08+912
MBZ | Bottom ballast | P2216-PMB-GQC-IR-06691-00 | CODE-5 | BOTTOM BALLAST
MBZ | Track laying | P2216-PMB-GQC-IR-04092-00 | CODE-1 | track laying | west | CH 00+580 ~ CH 01+400
MBZ | Track laying | P2216-PMB-GQC-IR-05432-00 | CODE-1 | track laying |  | CH 01+400 ~ CH 02+000
MBZ | Track laying | P2216-PMB-GQC-IR-05437-00 | CODE-5 | track laying |  | CH 02+000 ~ CH 02+468
MBZ | Track laying | P2216-PMB-GQC-IR-06493-00 | CODE-5 | track laying |  | CH 00+424 ~ CH 00+580
MBZ | Track laying | P2216-PMB-GQC-IR-04486-01 | CODE-5 | track laying | ZONE -05 | CH 03+296 ~ CH 05+150
MBZ | Track laying | P2216-PMB-GQC-IR-04919-00 | CODE-1 | track laying | ZONE -05
MBZ | Track laying | P2216-PMB-GQC-IR-05773-00 | CODE-1 | track laying | ZONE -01 | CH 01+600 ~ CH 02+600
MBZ | Track laying | P2216-PMB-GQC-IR-06019-01 | CODE-5 | track laying | ZONE -01 | CH 00+386 ~ CH 01+600
MBZ | Track laying | P2216-PMB-GQC-IR-06382-00 | CODE-1 | track laying | ZONE-09 | CH 08+500 ~ CH 08+875
MBZ | Track laying | P2216-PMB-GQC-IR-06383-00 | CODE-5 | track laying | ZONE-09
MBZ | Track laying | P2216-PMB-GQC-IR-06643-01 | CODE-1 | track laying | ZONE 6
MBZ | Track laying | P2216-PMB-GQC-IR-06644-00 | CODE-5 | track laying | ZONE 1
MBZ | Track laying | P2216-PMB-GQC-IR-06652-01 | CODE-5 | track laying | ZONE 7
MBZ | Track laying | P2216-PMB-GQC-IR-06653-00 | CODE-1 | track laying | ZONE 8
MBZ | Track laying | P2216-PMB-GQC-IR-06654-00 | CODE-5 | track laying | ZONE 9
MBZ | Track laying | P2216-PMB-GQC-IR-06705-00 | CODE-5 | track laying | ZONE 1&3 | CH 02+600 ~ CH 03+296
MBZ | Track laying | P2216-PMB-GQC-IR-06746-00 | CODE-1 | track laying | ZONE 1
MBZ | Track laying | P2216-PMB-GQC-IR-06747-00 | CODE-5 | track laying | ZONE 7 | CH 07+100 ~ CH 08+500
MBZ | Track laying | P2216-PMB-GQC-IR-06753-00 | CODE-1 | track laying | ZONE 7 | CH 06+000 ~ CH 07+100
MBZ | Track laying | P2216-PMB-GQC-IR-06865-00 | CODE-1 | track laying | ZONE 1
MBZ | Track laying | P2216-PMB-GQC-IR-06760-00 | CODE-1 | track laying |  | CH 05+150 ~ CH 06+000
MBZ | Track laying | P2216-PMB-GQC-IR-06874-00 | CODE-1 | track laying |  | CH 08+875 ~ CH 08+912
MBZ | Track laying | P2216-PMB-GQC-IR-06875-00 | CODE-5 | track laying
MBZ | Track laying | P2216-PMB-GQC-IR-07294-00 | CODE-1 | track laying | Zone 3 | CH 07+940 ~ CH 03+747
MBZ | MFBW | P2216-PMB-GQC-IR-05685-00 | CODE-5 | MFBW | WEST | CH 00+425 ~ CH 01+675
MBZ | MFBW | P2216-PMB-GQC-IR-05686-00 | CODE-5 | MFBW | WEST | CH 01+675 ~ CH 02+000
MBZ | MFBW | P2216-PMB-GQC-IR-05687-00 | CODE-1 | MFBW | WEST | CH 02+000 ~ CH 02+403
MBZ | MFBW | P2216-PMB-GQC-IR-06763-00 | CODE-5 | MFBW | WEST | CH 00+507 ~ CH 00+580
MBZ | MFBW | P2216-PMB-GQC-IR-04312-00 | CODE-1 | MFBW | ZONE 5
MBZ | MFBW | P2216-PMB-GQC-IR-04373-00 | CODE-5 | MFBW | ZONE 5 | CH 00+132
MBZ | MFBW | P2216-PMB-GQC-IR-04735-00 | CODE-5 | MFBW | ZONE 5 | CH 03+500 ~ CH 05+150
MBZ | MFBW | P2216-PMB-GQC-IR-06020-00 | CODE-5 | MFBW | ZONE 1 | CH 00+500 ~ CH 01+600
MBZ | MFBW | P2216-PMB-GQC-IR-06387-00 | CODE-5 | MFBW | ZONE 1 | CH 01+600 ~ CH 01+700
MBZ | MFBW | P2216-PMB-GQC-IR-06666-00 | CODE-1 | MFBW | ZONE 1, 3 | CH 01+700 ~ CH 03+500
MBZ | MFBW | P2216-PMB-GQC-IR-06385-00 | CODE-5 | MFBW | ZONE 9 | CH 08+500 ~ CH 08+875
MBZ | MFBW | P2216-PMB-GQC-IR-06384-00 | CODE-1 | MFBW | ZONE 9
MBZ | MFBW | P2216-PMB-GQC-IR-06656-00 | CODE-5 | MFBW | ZONE 5 | CH 02+000 ~ CH 02+403
MBZ | MFBW | P2216-PMB-GQC-IR-06684-00 | CODE-5 | MFBW | Zone 7
MBZ | MFBW | P2216-PMB-GQC-IR-06655-00 | CODE-1 | MFBW | zone 6
MBZ | MFBW | P2216-PMB-GQC-IR-06686-00 | CODE-5 | MFBW | Zone-7, 8, 9
MBZ | MFBW | P2216-PMB-GQC-IR-06750-00 | CODE-5 | MFBW | ZONE 1
MBZ | MFBW | P2216-PMB-GQC-IR-06761-00 | CODE-1 | MFBW | ZONE 6 | CH 05+150 ~ CH 06+600
MBZ | MFBW | P2216-PMB-GQC-IR-06728-00 | CODE-5 | MFBW | ZONE 7 | CH 06+600 ~ CH 08+240
MBZ | MFBW | P2216-PMB-GQC-IR-06762-00 | CODE-1 | MFBW | ZONE 1 | CH 00+470 ~ CH 00+545
MBZ | MFBW | P2216-PMB-GQC-IR-06779-00 | CODE-1 | MFBW | ZONE 3
MBZ | MFBW | P2216-PMB-GQC-IR-06831-00 | CODE-5 | MFBW | ZONE 1
MBZ | 1st tamping | P2216-PMB-GQC-IR-06268 | CODE-1 |  | Type-0
MBZ | 1st tamping | P2216-PMB-GQC-IR-06269 | CODE-1 |  | Type-0 | CH 69+742 ~ CH 69+842
MBZ | 1st tamping | P2216-PMB-GQC-IR-06270 | CODE-1 |  | Type-0 | CH 69+975 ~ CH 70+058
MBZ | 1st tamping | P2216-PMB-GQC-IR-06271 | CODE-5 |  | Type-0 | CH 00+150 ~ CH 00+250
MBZ | 1st tamping | P2216-PMB-GQC-IR-06272 | CODE-5 |  | Type-0 | CH 73+721 ~ CH 73+804
MBZ | 1st tamping | P2216-PMB-GQC-IR-06273 | CODE-5 |  | Type-0 | CH 73+497 ~ CH 73+580
MBZ | 1st tamping | P2216-PMB-GQC-IR-06274 | CODE-1 |  | Type-0
MBZ | 1st tamping | P2216-PMB-GQC-IR-06380 | CODE-1 |  | WEST | CH 00+424 ~ CH 02+468
MBZ | 1st tamping | P2216-PMB-GQC-IR-06702-00 | CODE-5 |  | Zone-5, 6, 8 & 9
MBZ | 1st tamping | P2216-PMB-GQC-IR-06710-00 | CODE-1 |  | zone -5
MBZ | 1st tamping | P2216-PMB-GQC-IR-06738-00 | CODE-1 |  | zone -1, 3,5 | CH 00+386 ~ CH 03+500
MBZ | 1st tamping | P2216-PMB-GQC-IR-06716-00 | CODE-5 |  | zone -5 | CH 03+500 ~ CH 05+070
MBZ | 1st tamping | P2216-PMB-GQC-IR-06784-00 | CODE-1 |  | ZONE 6 7 8 9 | CH 05+070 ~ CH 08+270
MBZ | 1st tamping | P2216-PMB-GQC-IR-06819-00 | CODE-1 |  | ZONE 9 | CH 08+270 ~ CH 08+912
MBZ | 1st tamping | P2216-PMB-GQC-IR-06823-00 | CODE-1
MBZ | 2nd tamping | P2216-PMB-GQC-IR-06307 | CODE-1 |  | MBZ Western Chord
MBZ | 2nd tamping | P2216-PMB-GQC-IR-06308 | CODE-1 |  | MBZ Western Chord | CH 69+742 ~ CH 69+842
MBZ | 2nd tamping | P2216-PMB-GQC-IR-06406 | CODE-1 |  | MBZ Western Chord | CH 69+975 ~ CH 70+058
MBZ | 2nd tamping | P2216-PMB-GQC-IR-06310 | CODE-5 |  | MBZ Eastern Chord | CH 00+150 ~ CH 00+250
MBZ | 2nd tamping | P2216-PMB-GQC-IR-06311 | CODE-5 |  | MBZ Eastern Chord | CH 73+721 ~ CH 73+804
MBZ | 2nd tamping | P2216-PMB-GQC-IR-06312 | CODE-5 |  | MBZ Eastern Chord | CH 73+497 ~ CH 73+580
MBZ | 2nd tamping | P2216-PMB-GQC-IR-06313 | CODE-1 |  | MBZ Eastern Chord
MBZ | 2nd tamping | P2216-PMB-GQC-IR-06494 | CODE-1 |  | ZONE 2&4 | CH 00+424 ~ CH 02+468
MBZ | 2nd tamping | P2216-PMB-GQC-IR-06703-00 | CODE-5 |  | Zone-5, 6, 8 & 9
MBZ | 2nd tamping | P2216-PMB-GQC-IR-06711-00 | CODE-5 |  | zone -5
MBZ | 2nd tamping | P2216-PMB-GQC-IR-06739-00 | CODE-2 |  | Zone-1 | CH 00+386 ~ CH 03+500
MBZ | 2nd tamping | P2216-PMB-GQC-IR-06717-00 | CODE-1 |  | zone -5 | CH 03+500 ~ CH 05+070
MBZ | 2nd tamping | P2216-PMB-GQC-IR-06785-00 | CODE-1 |  | ZONE 6 7 8 9 | CH 05+070 ~ CH 08+270
MBZ | 2nd tamping | P2216-PMB-GQC-IR-06820-00 | CODE-1 |  | ZONE 9 | CH 08+270 ~ CH 08+912
MBZ | 2nd tamping | P2216-PMB-GQC-IR-06824-00 | CODE-1
MBZ | 3rd tamping | P2216-PMB-GQC-IR-06404 | CODE-2 |  | MBZ Western Chord
MBZ | 3rd tamping | P2216-PMB-GQC-IR-06405 | CODE-2 |  | MBZ Western Chord | CH 69+742 ~ CH 69+842
MBZ | 3rd tamping | P2216-PMB-GQC-IR-06309 | CODE-2 |  | MBZ Western Chord | CH 69+975 ~ CH 70+058
MBZ | 3rd tamping | P2216-PMB-GQC-IR-06407 | CODE-5 |  | MBZ Eastern Chord | CH 00+150 ~ CH 00+250
MBZ | 3rd tamping | P2216-PMB-GQC-IR-06408 | CODE-5 |  | MBZ Eastern Chord | CH 73+721 ~ CH 73+804
MBZ | 3rd tamping | P2216-PMB-GQC-IR-06409 | CODE-5 |  | MBZ Eastern Chord | CH 73+497 ~ CH 73+580
MBZ | 3rd tamping | P2216-PMB-GQC-IR-06410 | CODE-2 |  | MBZ Eastern Chord
MBZ | 3rd tamping | P2216-PMB-GQC-IR-06495 | CODE-2 |  | ZONE 2&4 | CH 00+507 ~ CH 02+403
MBZ | 3rd tamping | P2216-PMB-GQC-IR-06704-00 | CODE-5 |  | Zone-5, 6, 8 & 9
MBZ | 3rd tamping | P2216-PMB-GQC-IR-06712-00 | CODE-5 |  | zone -5
MBZ | 3rd tamping | P2216-PMB-GQC-IR-06741-00 | CODE-2 |  | Zone-1 | CH 00+470 ~ CH 03+500
MBZ | 3rd tamping | P2216-PMB-GQC-IR-06821-00 | CODE-2 |  | ZONE 9 | CH 08+270 ~ CH 08+885
MBZ | Destressing of main line (MBZ | P2216-PMB-GQC-IR-06470-00 | CODE-1 |  | WEST | CH 01+600 ~ CH 02+468
MBZ | Destressing of main line (MBZ | P2216-PMB-GQC-IR-06700-00 | CODE-1 |  |  | CH 00+425 ~ CH 01+600
MBZ | Destressing of main line (MBZ | P2216-PMB-GQC-IR-06714-00 | CODE-1 |  | Zone-1 | CH 00+386 ~ CH 00+640
MBZ | Destressing of main line (MBZ | P2216-PMB-GQC-IR-06767-00 | CODE-1 |  | Zone 9
MBZ | Destressing of main line (MBZ | P2216-PMB-GQC-IR-06778-00 | CODE-1 |  | Zone 6
MBZ | Destressing of main line (MBZ | P2216-PMB-GQC-IR-06781-00 | CODE-1 |  | Zone 5 | CH 03+837 ~ CH 05+120
MBZ | Destressing of main line (MBZ | P2216-PMB-GQC-IR-06780-00 | CODE-1 |  | Zone 7 8 9
MBZ | Destressing of main line (MBZ | P2216-PMB-GQC-IR-06800-00 | CODE-1 |  | Zone 5 | CH 05+120 ~ CH 06+000
MBZ | Destressing of main line (MBZ | P2216-PMB-GQC-IR-06797-00 | CODE-1 |  | Zone 7 8 | CH 06+000 ~ CH 06+975
MBZ | Destressing of main line (MBZ | P2216-PMB-GQC-IR-06798-00 | CODE-1 |  | Zone 8 9 | CH 06+975 ~ CH 08+183
MBZ | Destressing of main line (MBZ | P2216-PMB-GQC-IR-06799-00 | CODE-1 |  | Zone 9 | CH 08+183 ~ CH 08+441
MBZ | Destressing of main line (MBZ | P2216-PMB-GQC-IR-06813-00 | CODE-1 |  | ZONE 9 | CH 08+441 ~ CH 08+912
MBZ | Destressing of main line (MBZ | P2216-PMB-GQC-IR-06827-00 | CODE-1 |  | ZONE 1 | CH 00+640 ~ CH 01+395
MBZ | Destressing of main line (MBZ | P2216-PMB-GQC-IR-06826-00 | CODE-1 |  | ZONE 1 | CH 01+395 ~ CH 02+500
MBZ | Destressing of main line (MBZ | P2216-PMB-GQC-IR-06828-00 | CODE-1 |  | ZONE 3 | CH 02+500 ~ CH 03+391
MBZ | Destressing of main line (MBZ | P2216-PMB-GQC-IR-06836-00 | CODE-1 |  | ZONE 5
MBZ | Destressing of main line (MBZ | P2216-PMB-GQC-IR-06838-00 | CODE-1 |  | ZONE 3
MBZ | Destressing of main line (MBZ | P2216-PMB-GQC-IR-06839-00 | CODE-1 |  | ZONE 1
MBZ | Destressing of main line (MBZ | P2216-PMB-GQC-IR-06840-00 | CODE-1 |  | ZONE 1
MBZ | Destressing of main line (MBZ | P2216-PMB-GQC-IR-06829-00 | CODE-1 |  | ZONE 3 | CH 03+391 ~ CH 03+605
MBZ | Destressing of main line (MBZ | P2216-PMB-GQC-IR-06830-00 | CODE-1 |  | ZONE 3 | CH 03+605 ~ CH 03+837
MBZ | Destressing of main line (MBZ | P2216-PMB-GQC-IR-06788-00 | CODE-1
MBZ | Destressing of main line (MBZ | P2216-PMB-GQC-IR-06811-00 | CODE-1
MBZ | Destressing of main line (MBZ | P2216-PMB-GQC-IR-06837-00 | CODE-1
MBZ | Destressing of turnout | P2216-PMB-GQC-IR-06306 | CODE-1
MBZ | Destressing of turnout | P2216-PMB-GQC-IR-06275 | CODE-1 |  |  | CH 69+691.90 ~ CH 69+841.90
MBZ | Destressing of turnout | P2216-PMB-GQC-IR-06276 | CODE-1 |  | Type-0 | CH 69+975.00 ~ CH 70+058.10
MBZ | Destressing of turnout | P2216-PMB-GQC-IR-06303 | CODE-1 |  |  | CH 00+150.00 ~ CH 00+300.00
MBZ | Destressing of turnout | P2216-PMB-GQC-IR-06304 | CODE-1 |  | Type-0 | CH 73+580.00 ~ CH 73+804.00
MBZ | Destressing of turnout | P2216-PMB-GQC-IR-06277 | CODE-1 |  | Type-0 | CH 73+496.90 ~ CH 73+580.00
MBZ | Destressing of turnout | P2216-PMB-GQC-IR-06305 | CODE-1
MBZ | Turnout installation | P2216-PMB-GQC-IR-06094-00 | CODE-1 |  | MBZ Western Chord
MBZ | Turnout installation | P2216-PMB-GQC-IR-06114-00 | CODE-1 |  | MBZ Western Chord | CH 69+841 ~ CH 69+925
MBZ | Turnout installation | P2216-PMB-GQC-IR-06115-00 | CODE-1 |  | MBZ Western Chord | CH 69+975 ~ CH 70+058
MBZ | Turnout installation | P2216-PMB-GQC-IR-06116-00 | CODE-1 |  | MBZ Eastern Chord | CH 00+150 ~ CH 00+233
MBZ | Turnout installation | P2216-PMB-GQC-IR-06117-00 | CODE-1 |  | MBZ Eastern Chord
MBZ | Turnout installation | P2216-PMB-GQC-IR-06119-00 | CODE-1 |  | MBZ Eastern Chord
MBZ | Turnout installation | P2216-PMB-GQC-IR-06120-00 | CODE-1 |  | MBZ Eastern Chord
MBZ | Turnout installation | P2216-PMB-GQC-IR-06474-00 | CODE-1 |  | ZONE-5 | CH 03+465.65 ~ CH 03+530.47
MBZ | Turnout installation | P2216-PMB-GQC-IR-06476-00 | CODE-1 |  | ZONE-1 | CH 03+695 ~ CH 03+759.82
MBZ | Turnout installation | P2216-PMB-GQC-IR-06477-00 | CODE-1 |  | ZONE-5
MBZ | Turnout installation | P2216-PMB-GQC-IR-06782-00 | CODE-1 |  | ZONE 9
MBZ | Turnout installation | P2216-PMB-GQC-IR-06783-00 | CODE-1 |  | ZONE 9
MBZ | Turnout installation | P2216-PMB-GQC-IR-06789-00 | CODE-1 |  | ZONE 9 | CH 08+258 ~ CH 08+301.20
MBZ | Turnout installation | P2216-PMB-GQC-IR-06790-00 | CODE-1
MBZ | ATW | P2216-PMB-GQC-IR-06249-00 | CODE-1
MBZ | ATW | P2216-PMB-GQC-IR-06257-00 | CODE-1
MBZ | ATW | P2216-PMB-GQC-IR-06258-00 | CODE-1
MBZ | ATW | P2216-PMB-GQC-IR-06259-00 | CODE-1
MBZ | ATW | P2216-PMB-GQC-IR-06260-00 | CODE-1
MBZ | ATW | P2216-PMB-GQC-IR-06261-00 | CODE-1
MBZ | ATW | P2216-PMB-GQC-IR-06262-00 | CODE-1
MBZ | ATW | P2216-PMB-GQC-IR-06671-00 | CODE-1
MBZ | ATW | P2216-PMB-GQC-IR-06672-00 | CODE-1
MBZ | ATW | P2216-PMB-GQC-IR-06673-00 | CODE-1
MBZ | ATW | P2216-PMB-GQC-IR-06736-00 | CODE-1
MBZ | ATW | P2216-PMB-GQC-IR-06727-00 | CODE-1
MBZ | ATW | P2216-PMB-GQC-IR-06726-00 | CODE-1
MBZ | ATW | P2216-PMB-GQC-IR-06810-00 | CODE-1
MBZ | ATW | P2216-PMB-GQC-IR-07896-00 | UR
MBZ | GR Installation | P2216-PMB-GQC-IR-07011-00 | CODE-1 |  |  | CH 07+861 ~ CH 07+933
MBZ | GR Installation | P2216-PMB-GQC-IR-07012-00 | CODE-1 |  |  | CH 07+407 ~ CH 07+726
MBZ | GR Installation | P2216-PMB-GQC-IR-07013-00 | CODE-1 |  |  | CH 07+407
MBZ | GR Installation | P2216-PMB-GQC-IR-07013-00 | CODE-1 |  |  | CH 06+883 ~ CH 06+959
MBZ | GR Installation | P2216-PMB-GQC-IR-07014-00 | CODE-5 |  |  | CH 02+590 ~ CH 03+114
MBZ | GR Installation | P2216-PMB-GQC-IR-07015-00 | CODE-5 |  |  | CH 05+355 ~ CH 06+110
MBZ | GR Installation | P2216-PMB-GQC-IR-07016-00 | CODE-5 |  | WESTERN CHORD | CH 01+663 ~ CH 02+059
MBZ | GR Installation | P2216-PMB-GQC-IR-07017-00 | CODE-1 |  |  | CH 02+590 ~ CH 03+114
MBZ | Final tamping | P2216-PMB-GQC-IR-06314 | CODE-1 |  | MBZ Western Chord
MBZ | Final tamping | P2216-PMB-GQC-IR-06315 | CODE-1 |  | MBZ Western Chord | CH 69+742 ~ CH 69+842
MBZ | Final tamping | P2216-PMB-GQC-IR-06316 | CODE-1 |  | MBZ Western Chord | CH 69+975 ~ CH 70+058
MBZ | Final tamping | P2216-PMB-GQC-IR-06321 | CODE-1 |  | MBZ Eastern Chord | CH 00+150 ~ CH 00+250
MBZ | Final tamping | P2216-PMB-GQC-IR-06322 | CODE-1 |  | MBZ Eastern Chord | CH 73+721 ~ CH 73+804
MBZ | Final tamping | P2216-PMB-GQC-IR-06323 | CODE-1 |  | MBZ Eastern Chord | CH 73+497 ~ CH 73+580
MBZ | Final tamping | P2216-PMB-GQC-IR-06324 | CODE-1 |  | MBZ Eastern Chord
MBZ | Final tamping | P2216-PMB-GQC-IR-06713-00 | CODE-1 |  | zone -5
MBZ | Final tamping | P2216-PMB-GQC-IR-06719-00 | CODE-1 |  | zone -5 | CH 00+386 ~ CH 08+885
MBZ | Final tamping | P2216-PMB-GQC-IR-06748-00 | CODE-1 |  | West | CH 00+425 ~ CH 02+468
MBZ | Ballastprofiling | P2216-PMB-GQC-IR-07020-00 | CODE-1 |  | western chord | CH 00+425.000 ~ CH 02+468.000
MBZ | Ballastprofiling | P2216-PMB-GQC-IR-07021-00 | CODE-1 |  |  | CH 00+386.000 ~ CH 08+912.000
MBZ | Ballastprofiling | P2216-PMB-GQC-IR-07022-00 | CODE-1
MBZ | Rail flaw detection | P2216-PMB-GQC-IR-07040-00 | CODE-2 |  | western chrod | CH 00+424.000 ~ CH 02+468.000
MBZ | Rail flaw detection | P2216-PMB-GQC-IR-07032-00 | CODE-2 |  |  | CH 00+385.000 ~ CH 02+500.000
MBZ | Rail flaw detection | P2216-PMB-GQC-IR-07519-00 | CODE-2
MBZ | Buffer Stop | P2216-PMB-GQC-IR-07037-00 | CODE-2
MBZ | Buffer Stop | P2216-PMB-GQC-IR-07038-00 | CODE-2
MBZ | Ex track removal | P2216-PMB-GQC-IR-06125-00 | CODE-1 |  | MBZ Western Chord
MBZ | Ex track removal | P2216-PMB-GQC-IR-06126-00 | CODE-1 |  | MBZ Western Chord | CH 69+819 ~ CH 69+925
MBZ | Ex track removal | P2216-PMB-GQC-IR-06128-00 | CODE-1 |  | MBZ Western Chord | CH 69+975 ~ CH 70+051
MBZ | Ex track removal | P2216-PMB-GQC-IR-06129-00 | CODE-1 |  | MBZ Eastern Chord | CH 00+044 ~ CH 00+150
MBZ | Ex track removal | P2216-PMB-GQC-IR-06130-00 | CODE-1 |  | MBZ Eastern Chord | CH 73+721 ~ CH 73+827
MBZ | Ex track removal | P2216-PMB-GQC-IR-06132-00 | CODE-1 |  | MBZ Eastern Chord
MBZ | Ex track removal | P2216-PMB-GQC-IR-06131-01 | CODE-1 |  | MBZ Eastern Chord | CH 73+580 ~ CH 73+497
MBZ | SURVEY WORK | P2216-PMB-GQC-IR-06628-00 | CODE-1 | Control Point | MBZ Section | Qty：43
MBZ | Structure gauge inspection | P2216-PMB-GQC-IR-6985 | CODE-1
MBZ | Sign markers | P2216-S04-GQC-IR-07069-00 | CODE-1 |  |  | CH 00+386.000 ~ CH 08+912.000
MBZ | Sign markers | P2216-S04-GQC-IR-07070-00 | CODE-1
MBZ | Sign markers | P2216-S04-GQC-IR-07071-00 | CODE-1 |  | western chord
MBZ | Datum plate | P2216-S04-GQC-IR-07096-00 | UR |  |  | CH 02+620.000 ~ CH 07+660.000
MBZ | Datum plate | P2216-S04-GQC-IR-07546-00 | CODE-1 |  | western chord
JBL | Ballast mats | P2216-S04-GQC-IR-00025-00 | CODE-1 | BALLAST MATS | JBL TRACK 1
JBL | Ballast mats | P2216-S04-GQC-IR-00075-00 | CODE-1 | BALLAST MATS | JBL TRACK 2 | CH 11+181.990 ~ CH 11+525.370
JBL | Ballast mats | P2216-S04-GQC-IR-00023-00 | CODE-1 | BALLAST MATS | EXPO STATION | CH 11+525.370 ~ CH 11+601.760
JBL | Ballast mats | P2216-S04-GQC-IR-00076-00 | CODE-5 | BALLAST MATS | JBL TRACK 1
JBL | Ballast mats | P2216-S04-GQC-IR-00077-00 | CODE-5 | BALLAST MATS | EXPO STATION
JBL | Ballast mats | P2216-S04-GQC-IR-00024-00 | CODE-1 | BALLAST MATS | EXPO STATION
JBL | Ballast mats | P2216-S04-GQC-IR-00093-00 | CODE-5 | BALLAST MATS | EXPO STATION | CH 11+887.190 ~ CH 11+979.540
JBL | Bottom ballast | P2216-S04-GQC-IR-00068-00 | CODE-1 |  | Dubai station | CH 11+525.378 ~ CH 12+160.115
JBL | Bottom ballast | P2216-S04-GQC-IR-00069-00 | CODE-5 |  | Dubai station
JBL | Track laying | P2216-S04-GQC-IR-00050-00 | CODE-1 |  | JBL
JBL | Track laying | P2216-S04-GQC-IR-00059-00 | CODE-5 |  | JBL
JBL | Track laying | P2216-S04-GQC-IR-00066-00 | CODE-5 |  | Dubai station
JBL | Track laying | P2216-S04-GQC-IR-00067-00 | CODE-5 |  | Dubai station | CH 11+525.378 ~ CH 12+160.115
JBL | Track laying | P2216-S04-GQC-IR-00094-00 | CODE-1 |  | JBL | CH 10+720.000 ~ CH 11+525.378
JBL | Track laying | P2216-S04-GQC-IR-00107-00 | CODE-1 |  | JBL
JBL | MFBW | P2216-S04-GQC-IR-00065-00 | CODE-1 |  | JBL | CH 04+340 ~ CH 05+415
JBL | MFBW | P2216-S04-GQC-IR-00070-00 | CODE-5 |  | JBL | CH 05+415 ~ CH 06+630
JBL | MFBW | P2216-S04-GQC-IR-00072-00 | CODE-5 |  | JBL | CH 06+630 ~ CH 08+504
JBL | MFBW | P2216-S04-GQC-IR-00073-00 | CODE-5 |  | JBL | CH 08+504 ~ CH 09+630
JBL | MFBW | P2216-S04-GQC-IR-00074-00 | CODE-5 |  | JBL | CH 09+700 ~ CH 10+640
JBL | MFBW | P2216-S04-GQC-IR-00099-00 | CODE-1 |  | JBL | CH 10+640 ~ CH 11+521
JBL | MFBW | P2216-S04-GQC-IR-00100-00 | CODE-5 |  | EXPO | CH 11+521 ~ CH 12+155
JBL | MFBW | P2216-S04-GQC-IR-00101-00 | CODE-5 |  | JBL
JBL | MFBW | P2216-S04-GQC-IR-00102-00 | CODE-5 |  | EXPO
JBL | MFBW | P2216-S04-GQC-IR-00156-00 | CODE-1 |  | JBL
JBL | 1st tamping | P2216-S04-GQC-IR-00027-00 | CODE-1 |  | JBL
JBL | 1st tamping | P2216-S04-GQC-IR-00038-00 | CODE-5 |  | JBL | CH 09+480.000 ~ CH 09+823.195
JBL | 1st tamping | P2216-S04-GQC-IR-00042-00 | CODE-5 |  | JBL
JBL | 1st tamping | P2216-S04-GQC-IR-00056-00 | CODE-5 |  | JBL | CH 04+100.000 ~ CH 04+465.000
JBL | 1st tamping | P2216-S04-GQC-IR-00078-00 | CODE-1 |  | JBL | CH 04+250.000 ~ CH 10+100.000
JBL | 1st tamping | P2216-S04-GQC-IR-00081-00 | CODE-5 |  | JBL | CH 10+100.000 ~ CH 11+520.000
JBL | 1st tamping | P2216-S04-GQC-IR-00084-00 | CODE-5 |  | EXPO | CH 11+520.000 ~ CH 12+155.097
JBL | 1st tamping | P2216-S04-GQC-IR-00087-00 | CODE-5 |  | JBL
JBL | 1st tamping | P2216-S04-GQC-IR-00090-00 | CODE-1 |  | EXPO
JBL | 2nd tamping | P2216-S04-GQC-IR-00035-00 | CODE-1 |  | JBL
JBL | 2nd tamping | P2216-S04-GQC-IR-00039-00 | CODE-5 |  | JBL | CH 09+480.000 ~ CH 09+823.195
JBL | 2nd tamping | P2216-S04-GQC-IR-00043-00 | CODE-5 |  | JBL
JBL | 2nd tamping | P2216-S04-GQC-IR-00055-00 | CODE-5 |  | JBL | CH 04+100.000 ~ CH 04+465.000
JBL | 2nd tamping | P2216-S04-GQC-IR-00079-00 | CODE-1 |  | JBL | CH 04+250.000 ~ CH 10+100.000
JBL | 2nd tamping | P2216-S04-GQC-IR-00082-00 | CODE-1 |  | JBL | CH 10+100.000 ~ CH 11+520.000
JBL | 2nd tamping | P2216-S04-GQC-IR-00085-00 | CODE-5 |  | EXPO | CH 11+520.000 ~ CH 12+155.097
JBL | 2nd tamping | P2216-S04-GQC-IR-00088-00 | CODE-5 |  | JBL
JBL | 2nd tamping | P2216-S04-GQC-IR-00091-00 | CODE-5 |  | EXPO
JBL | Destressing | P2216-S04-GQC-IR-00048-00 | CODE-1 |  | JBL | CH 09+532 ~ CH 09+875
JBL | Destressing | P2216-S04-GQC-IR-00052-00 | CODE-1 |  | JBL | CH 10+570 ~ CH 10+913
JBL | Destressing | P2216-S04-GQC-IR-00095-00 | CODE-1 |  | JBL
JBL | Destressing | P2216-S04-GQC-IR-00096-00 | CODE-1 |  | JBL
JBL | Destressing | P2216-S04-GQC-IR-00097-00 | CODE-1 |  | JBL
JBL | Destressing | P2216-S04-GQC-IR-00122-00 | CODE-1 |  | JBL
JBL | Destressing | P2216-S04-GQC-IR-00114-00 | CODE-1 |  | EXPO
JBL | Destressing | P2216-S04-GQC-IR-00115-00 | CODE-1 |  | EXPO | CH 11+525 ~ CH 12+160
JBL | Destressing | P2216-S04-GQC-IR-00116-00 | CODE-1 |  | JBL
JBL | Destressing | P2216-S04-GQC-IR-00117-00 | CODE-1 |  | JBL | CH 10+998 ~ CH 11+525
JBL | Destressing | P2216-S04-GQC-IR-00118-00 | CODE-1 |  | JBL | CH 10+720 ~ CH 10+998
JBL | Destressing | P2216-S04-GQC-IR-00123-00 | CODE-1 |  | JBL
JBL | Destressing | P2216-S04-GQC-IR-00124-00 | CODE-1 |  | JBL
JBL | Destressing | P2216-S04-GQC-IR-00125-00 | CODE-1 |  | JBL
JBL | Turnout installation | P2216-S04-GQC-IR-00033-00 | CODE-1 |  | JBL | CH 09+630 ~ CH 09+673
JBL | Turnout installation | P2216-S04-GQC-IR-00026-00 | CODE-1 |  | JBL
JBL | Turnout installation | P2216-S04-GQC-IR-00046-00 | CODE-1 |  | JBL
JBL | Turnout installation | P2216-S04-GQC-IR-00049-00 | CODE-1 |  | JBL | CH 04+250 ~ CH 04+315
JBL | Turnout installation | P2216-S04-GQC-IR-00110-00 | CODE-1 |  | EXPO
JBL | Turnout installation | P2216-S04-GQC-IR-00111-00 | CODE-1 |  | EXPO | CH 11+702 ~ CH 11+737
JBL | Turnout installation | P2216-S04-GQC-IR-00112-00 | CODE-1 |  |  | CH 10+935 ~ CH 10+989
JBL | Turnout installation | P2216-S04-GQC-IR-00113-00 | CODE-1
JBL | ATW | P2216-S04-GQC-IR-00047-00 | CODE-1 |  |  | CH 09+630 ~ CH 09+673
JBL | ATW | P2216-S04-GQC-IR-00034-00 | CODE-1
JBL | ATW | P2216-S04-GQC-IR-00053-00 | CODE-1
JBL | ATW | P2216-S04-GQC-IR-00054-00 | CODE-1 |  |  | 04+250.00 ~ 04+315.00
JBL | ATW | P2216-S04-GQC-IR-00098-00 | CODE-1
JBL | ATW | P2216-S04-GQC-IR-00119-00 | CODE-1
JBL | ATW | P2216-S04-GQC-IR-00120-00 | CODE-1
JBL | ATW | P2216-S04-GQC-IR-00121-00 | CODE-1
JBL | ATW | P2216-S04-GQC-IR-00139-00 | CODE-1
JBL | GR Installation | P2216-S04-GQC-IR-00131-00 | CODE-1 |  | JBL
JBL | GR Installation | P2216-S04-GQC-IR-00132-00 | CODE-1 |  | JBL
JBL | GR Installation | P2216-S04-GQC-IR-00133-00 | CODE-1 |  | JBL | CH 11+175 ~ CH 11+525
JBL | GR Installation | P2216-S04-GQC-IR-00134-00 | CODE-1 |  | JBL
JBL | GR Installation | P2216-S04-GQC-IR-00135-00 | CODE-1 |  | JBL
JBL | GR Installation | P2216-S04-GQC-IR-00136-00 | CODE-1 |  | EXPO | CH 11+525 ~ CH 11+599
JBL | GR Installation | P2216-S04-GQC-IR-00137-00 | CODE-1 |  | EXPO
JBL | Final tamping | P2216-S04-GQC-IR-00037-00 | CODE-1 |  | JBL
JBL | Final tamping | P2216-S04-GQC-IR-00041-00 | CODE-1 |  | JBL | CH 09+480 ~ CH 09+823
JBL | Final tamping | P2216-S04-GQC-IR-00045-00 | CODE-1 |  | JBL
JBL | Final tamping | P2216-S04-GQC-IR-00058-00 | CODE-1 |  | JBL | CH 04+100 ~ CH 04+465
JBL | Final tamping | P2216-S04-GQC-IR-00063-00 | CODE-1 |  | JBL | CH 10+570 ~ CH 10+913
JBL | Final tamping | P2216-S04-GQC-IR-00103-00 | CODE-1 |  | JBL | CH 04+250 ~ CH 11+521
JBL | Final tamping | P2216-S04-GQC-IR-00104-00 | CODE-1 |  | JBL
JBL | Final tamping | P2216-S04-GQC-IR-00105-00 | CODE-1 |  | EXPO | CH 11+521 ~ CH 12+155
JBL | Final tamping | P2216-S04-GQC-IR-00106-00 | CODE-1 |  | EXPO
JBL | REJ | P2216-S04-GQC-IR-00138-00 | CODE-2 |  | JBL
JBL | Ballast profiling | P2216-S04-GQC-IR-00126-00 | CODE-1 |  | JBL
JBL | Ballast profiling | P2216-S04-GQC-IR-00127-00 | CODE-1 |  | JBL | CH 10+720.000 ~ CH 11+525.378
JBL | Ballast profiling | P2216-S04-GQC-IR-00128-00 | CODE-1 |  | EXPO
JBL | Ballast profiling | P2216-S04-GQC-IR-00129-00 | CODE-1 |  | EXPO | CH 11+525.378 ~ CH 12+160.115
JBL | Rail flaw detection | P2216-S04-GQC-IR-00140-00 | CODE-2 |  | JBL
JBL | Rail flaw detection | P2216-S04-GQC-IR-00141-00 | CODE-2 |  | JBL
JBL | Rail flaw detection | P2216-S04-GQC-IR-00142-00 | CODE-2 |  | EXPO
JBL | Rail flaw detection | P2216-S04-GQC-IR-00143-00 | CODE-2 |  | EXPO
JBL | Buffer Stop | P2216-S04-GQC-IR-00162-00 | CODE-2
JBL | Buffer Stop | P2216-S04-GQC-IR-00163-00 | CODE-2 |  |  | 12+130
JBL | Existing track removal (JBL | P2216-S04-GQC-IR-00029-00 | CODE-5
JBL | Existing track removal (JBL | P2216-S04-GQC-IR-00030-00 | CODE-5
JBL | Existing track removal (JBL | P2216-S04-GQC-IR-00031-00 | CODE-5 |  |  | 04+250 ~ 04+331.6
JBL | SURVEY WORK | P2216-S04-GQC-IR-00155-00 | CODE-1 | control point | EXPO | Qty:5
JBL | SURVEY WORK | P2216-S04-GQC-IR-00151-00 | CODE-1 | control point | JBL | Qty:4
JBL | Structure gauge inspection | P2216-S04-GQC-IR-00158-00 | CODE-2 |  | EXPO
JBL | Structure gauge inspection | P2216-S04-GQC-IR-00160-00 | draft |  | JBL | CH 04+425.000 ~ CH 11+521.000
JBL | DTS 1st | P2216-S04-GQC-IR-00144-00 | CODE-1
JBL | DTS 1st | P2216-S04-GQC-IR-00145-00 | CODE-1
JBL | DTS 1st | P2216-S04-GQC-IR-00146-00 | CODE-1 |  | EXPO
JBL | DTS 1st | P2216-S04-GQC-IR-00147-00 | CODE-1 |  | JBL | CH 10+763 ~ CH 11+525
JBL | DTS 1st | P2216-S04-GQC-IR-00148-00 | CODE-1 |  | EXPO | CH 11+525 ~ CH 12+160.115
JBL | DTS 2nd | P2216-S04-GQC-IR-00149-00 | CODE-1
JBL | DTS 2nd | P2216-S04-GQC-IR-00150-00 | CODE-1
JBL | DTS 2nd | P2216-S04-GQC-IR-00152-00 | CODE-1 |  | EXPO
JBL | DTS 2nd | P2216-S04-GQC-IR-00153-00 | CODE-1 |  | JBL | CH 10+763 ~ CH 11+525
JBL | DTS 2nd | P2216-S04-GQC-IR-00154-00 | CODE-1 |  | EXPO | CH 11+525 ~ CH 12+160.115
JBL | Fouling point | P2216-S04-GQC-IR-00166-00 | CODE-1 |  | EXPO
JBL | Fouling point | P2216-S04-GQC-IR-00165-00 | CODE-1 |  | JBL
Fujairah Station | Track Laying | P2216-S04-GQC-IR-00004-00 | CODE-1 | TRACK LAYING
Fujairah Station | Ballast MATS | P2216-S04-GQC-IR-00005-00 | CODE-2 | Ballast MATS
Fujairah Station | Ballast MATS | P2216-S04-GQC-IR-00157-00 | CODE-5 | Ballast MATS
Fujairah Station | Turnout Installation | P2216-S04-GQC-IR-00006-00 | CODE-1 | Turnout Installation
Fujairah Station | MFBW | P2216-S04-GQC-IR-00008-00 | CODE-1 | MFBW
Fujairah Station | Turnout 1st Tamping | P2216-S04-GQC-IR-00009-00 | CODE-5 | Turnout 1st tamping
Fujairah Station | Turnout 2nd Tamping | P2216-S04-GQC-IR-00010-00 | CODE-5 | Turnout 2nd tamping
Fujairah Station | Turnout 3rd Tamping | P2216-S04-GQC-IR-00011-00 | CODE-5 | Turnout 3rd tamping
Fujairah Station | Turnout Final Tamping | P2216-S04-GQC-IR-00012-00 | CODE-1 | Turnout Final Tamping
Fujairah Station | ATW | P2216-S04-GQC-IR-00013-00 | CODE-1 | ATW
Fujairah Station | Turnout De-stressing | P2216-S04-GQC-IR-00014-00 | CODE-1 | Turnout de-stressing
Fujairah Station | De-streesing Of Rail | P2216-S04-GQC-IR-00015-00 | CODE-1 | De-streesing of Rail
Fujairah Station | 1sttamping | P2216-S04-GQC-IR-00016-00 | CODE-5 | 1stTamping
Fujairah Station | 2nd Tamping | P2216-S04-GQC-IR-00017-00 | CODE-5 | 2nd Tamping
Fujairah Station | 3rd Tamping | P2216-S04-GQC-IR-00018-00 | CODE-5 | 3rd Tamping
Fujairah Station | Final Tamping | P2216-S04-GQC-IR-00019-00 | CODE-1 | Final Tamping
Fujairah Station | Ballast Profilling | P2216-S04-GQC-IR-00020-00 | CODE-1 | Ballast Profilling
Fujairah Station | Control Point | P2216-S04-GQC-IR-00021-00 | CODE-1 | CONTROL POINT
Fujairah Station | Fujairah Clearance And Fouling Marker | P2216-S04-GQC-IR-00164-00 | CODE-1 | Fujairah clearance and fouling marker
Fujairah Station | Structural Gauge | P2216-S04-GQC-IR-00168-00 | CODE-1 | Structural gauge
Fujairah Station | Track Maker | P2216-S04-GQC-IR-00170-00 | CODE-1 | Track maker
Fujairah Station | Existing Track Removal | P2216-S04-GQC-IR-00171-00 | CODE-1 | Existing track removal
Fujairah Station | Buffer Stop | P2216-S04-GQC-IR-00130-00 | CODE-2 | buffer stop
Fujairah Loop | Existing Track Removal | P2435-HJR-GQC-IR-0034-00 | UR | Existing Track removal | HJR19A | CH 48+887
Fujairah Loop | Existing Track Removal | N/A | UR | Existing Track removal | HJR19B | CH 50+942
Fujairah Loop | Track Laying | P2435-HJR-GQC-IR-0036-00 | UR | Track laying | HJR | CH 48+927
Fujairah Loop | Ballast Mat | P2435-HJR-GQC-IR-0035-00 | UR | ballast mat | HJR | CH 50+200
Fujairah Loop | Turnout Installation | P2435-HJR-GQC-IR-0037-00 | UR | Turnout Installation | HJR | CH 48+887
Fujairah Loop | MFBW | P2435-HJR-GQC-IR-0039-00 | UR | MFBW | HJR | CH 48+921
Fujairah Port | Existing Track Removal | P2435-FJP-GQC-IR-00001 | 未匹配到对应code | Existing Track removal | FPJ 01A | CH 55+002
Fujairah Port | Track Laying | P2435-FJP-GQC-IR-00004 | 未匹配到对应code | Track laying | FJP | CH 55+543
Fujairah Port | Bottom Ballast | P2435-FJP-GQC-IR-00003 | 未匹配到对应code | bottom ballast | FJP | CH 55+543
Fujairah Port | Bottom Ballast | P2435-FJP-GQC-IR-00002 | 未匹配到对应code | bottom ballast | FJP | CH 55+043
Fujairah Port | Track Laying | P2435-FJP-GQC-IR-00005 | 未匹配到对应code | Track laying | FJP | CH 55+043
Fujairah Port | 1st_tamping | P2435-FJP-GQC-IR-00006 | 未匹配到对应code | 1st_Tamping | FJP | CH 55+002
Fujairah Port | 2nd_tamping | P2435-FJP-GQC-IR-00007 | 未匹配到对应code | 2nd_Tamping | FJP | CH 55+002
Fujairah Port | Fin_tamping | N/A | UR | Fin_Tamping | FJP | CH 55+002
Fujairah Port | MFBW | P2435-FJP-GQC-IR-00008 | 未匹配到对应code | MFBW | FJP | CH 55+543
LIWA | Track Laying | P2414-GMC-GQC-IR-00243 | CODE-2 | TRACK LAYING
LIWA | Track Laying | P2414-GMC-GQC-IR-00251 | CODE-2 | TRACK LAYING
LIWA | Track Laying | P2414-GMC-GQC-IR-00253 | CODE-2 | TRACK LAYING
LIWA | Bottom Ballast | P2414-GMC-GQC-IR-00244 | CODE-2 | Bottom Ballast
LIWA | Existing Track Ramoval | P2414-GMC-GQC-IR-00245 | CODE-2 | existing track ramoval
LIWA | Existing Track Ramoval | P2414-GMC-GQC-IR-00254 | CODE-2 | existing track ramoval
LIWA | Turnout Installation | P2414-GMC-GQC-IR-00247 | CODE-2 | Turnout Installation | GMC01
LIWA | Turnout Installation | P2414-GMC-GQC-IR-00256 | UR | Turnout Installation | SHA01
LIWA | ATW | P2414-GMC-GQC-IR-00257 | CODE-2 | ATW | GMC01
LIWA | Turnout Destressing | P2414-GMC-GQC-IR-00258 | CODE-2 | Turnout Destressing | GMC01
LIWA | 1st Tamping | P2414-GMC-GQC-IR-00259 | CODE-4 | 1st Tamping | GMC01
LIWA | 2rd Tamping | P2414-GMC-GQC-IR-00260 | CODE-4 | 2rd Tamping | GMC01
LIWA | Fintamping | P2414-GMC-GQC-IR-00261 | CODE-4 | FinTamping | GMC01
PL-28 | Track Laying | P2216-DMB-GQC-IR-00360 | CODE-2 | TRACK LAYING
PL-28 | Bottom Ballast | P2216-DMB-GQC-IR-00328 | draft | Bottom Ballast
PL-28 | Bottom Ballast | P2216-DMB-GQC-IR-00359 | UR | Bottom Ballast